## Sheet1
Code site | Nom du site | Expan / New | OCM Batch Name | Region | Delivery_Status | On-Air Date | ToAddLayers | Priortity | Comment | Material status | Status
CTR_859 | NSEM | New | Regulatory - New |  | on air | 2025-10-15 | G9U9L8L7 |  | On air |  | On air
SUD_120 | NTAM | New | Regulatory - New |  | on air | 2025-03-10 | G9U9L8L7 |  | On air |  | On air
SUD_206 | Sanglou | New | Regulatory - New |  | on air | 2025-03-24 | G9U9L8L7 |  | On air |  | On air
SUD_205 | LELE-IHS | New | Regulatory - New |  | on air | 2025-04-25 | G9U9L8L7 |  | On air |  | On air
SUD_204 | ODING | New | Regulatory - New |  | on air | 2025-03-24 | G9U9L8L7 |  | On air |  | On air
CTR_904 | AFANLOUM | New | Regulatory - New |  | on air | 2025-07-17 | G9U9L8L7 |  | On air |  | On air
SUD_164 | Tho-II | New | Regulatory - New |  | on air | 2025-01-13 | G9U9L8L7 |  | On air |  | On air
CTR_891 | Nkoambang | New | Regulatory - New |  | on air | 2025-03-09 | G9U9L8L7 |  | On air |  | On air
SUD_161 | NTENYING1 | New | Regulatory - New |  | on air | 2025-03-12 | G9U9L8L7 |  | On air |  | On air
CTR_981 | Mvamebod | New | Regulatory - New |  | on air | 2025-04-18 | G9U9L8L7 |  | On air |  | On air
EST_185 | Ndoumbi | New | Regulatory - New |  | on air | 2025-01-02 | G9U9L8L7 |  | On air |  | On air
CTR_860 | Mvam-Yétom | New | Regulatory - New |  | on air | 2025-03-09 | G9U9L8L7 |  | On air |  | On air
SUD_163 | MELEN-MINTOM | New | Regulatory - New |  | on air | 2025-01-31 | G9U9L8L7 |  | On air |  | On air
SUD_159 | Lele | New | Regulatory - New |  | on air | 2025-01-15 | G9U9L8L7 |  | On air |  | On air
SUD_162 | Essang-MVOUT | New | Regulatory - New |  | on air | 2024-12-31 | G9U9L8L7 |  | On air |  | On air
SUD_160 | EMVIEMG1 | New | Regulatory - New |  | on air | 2025-04-17 | G9U9L8L7 |  | On air |  | On air
CTR_938 | Akonolinga_New IHS | New | Regulatory - New |  | on air | 2025-02-28 | G9U9L8L7 |  | On air |  | On air
NRD_198 | VogZom | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_188 | Meyo-Essakoe | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
EST_271 | Bipindi Mvile | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
EST_268 | Mobesso-Kobi | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
CTR_1041 | Carrefour-TIGA | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_131 | Nkolatom | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_181 | Doungou | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
EST_208 | Mboulaye | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
ADM_226 | Dir-Samaki | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
EXN_388 | Glem | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
EXN_387 | Lakta | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
CTR_977 | Dog-Nlend | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
CTR_860 | NYAKOKOMBO | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
CTR_980 | Nkong-Massa | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_165 | Koumyetotan | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
EST_270 | Banga-Ndelele | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_289 | Fenda-Mintange | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_288 | Nemeyong | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_287 | Nlozok | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
CTR_1113 | Mbango-Boulou | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_183 | Bandevouri | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_286 | Ababita | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_285 | Nkolngbwa | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
ADM_257 | Mbeng-Ngoumi | New | Regulatory - New |  | Outbound |  | G9U9L8L7 |  | Outbound |  | Pending Material
ADM_256 | Mbeng-Ribao | New | Regulatory - New |  | Outbound |  | G9U9L8L7 |  | Outbound |  | Pending Material
ADM_255 | Mbeng-Ndanga | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
ADM_253 | Touboro-Gop | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
ADM_201 | Kéla-Sami | New | Regulatory - New |  | Outbound |  | G9U9L8L7 |  | Outbound |  | Pending Material
ADM_223 | Bekasiki-Guizore | New | Regulatory - New |  | Outbound |  | G9U9L8L7 |  | Outbound |  | Pending Material
ADM_252 | Mahor | New | Regulatory - New |  | Outbound |  | G9U9L8L7 |  | Outbound |  | Pending Material
CTR_1119 | Ngouassabe | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
ADM_251 | Nyadjinda | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
CTR_1118 | Sengbe | New | Regulatory - New |  | Outbound |  | G9U9L8L7 |  | Outbound |  | Pending Material
CTR_987 | Mankim | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | RFI Planned |  | Pending Material
CTR_986 | Djereing | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | RFI Planned |  | Pending Material
CTR_985 | Djampa | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | Waiting RFI |  | Waiting RFI
SUD_166 | koumyetotan-Olong | New | Regulatory - New |  | MOS Ongoing |  | G9U9L8L7 |  | Ongoing as Planned |  | Ongoing as Planned
CTR_1112 | Mbalmayo-Akoumetam | New | Regulatory - New |  | Planned |  | G9U9L8L7 |  | RFI Planned |  | Pending Material
EST_269 | Ayos-Efoulan | New | Regulatory - New |  | MOS Ongoing |  | G9U9L8L7 |  | Ongoing as Planned |  | Ongoing as Planned
ADM_254 | Ambarang | New | Regulatory - New |  | Outbound |  | G9U9L8L7 |  | Outbound |  | Pending Material
EST_267 | Ndanga-Ndengue | New | Regulatory - New |  | MOS Done |  | G9U9L8L7 |  | Ongoing as Planned |  | Ongoing as Planned